## Data
Date | Pool | ODEA Phase | Ritual | Artifact | Result | Link | Understand what people need | Address the whole experience, from start to finish | Make it simple and intuitive | Build the service using agile and iterative practices | Structure budgets and contracts to support delivery | Assign one leader and hold that person accountable | Bring in experienced teams | Choose a modern technology stack | Deploy in a flexible hosting environment | Automate testing and deployments | Manage security and privacy through reusable processes | Use data to drive decisions | Default to open
2015-06-18 | One | Discovery | User Story Development | Enterprise Context | Research FDA and regulatory burden issues and drivers | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Discovery%20and%20Requirements%20Analysis.docx | X | X |  |  |  | X | X |  |  |  |  | X
2015-06-18 | One | Discovery | User Story Development | Enterprise Context | Document preliminary context for persona and scenarios | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Discovery%20and%20Requirements%20Analysis.docx | X | X |  |  |  | X | X |  |  |  |  | X
2015-06-18 | One | Discovery |  | Vision Statement | Research FDA and regulatory burden issues and drivers | https://github.com/binarygroup/OpenFDADesign/tree/master/Documents/Issues%20and%20Drivers | X | X |  |  |  | X | X |  |  |  |  | X
2015-06-19 | One | Discovery | User Story Development | Enterprise Context | Meet with user SMEs | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Discovery%20and%20Requirements%20Analysis.docx | X | X | X |  |  | X | X |  |  |  |  | X
2015-06-19 | One | Discovery | User Story Development | Product Backlog | Developed initial product backlog | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Discovery%20and%20Requirements%20Analysis.docx | X | X | X |  |  | X | X |  |  |  |  | X
2015-06-19 | One | Decision Strategy | User Story Development | Prototype | Develop design prototype v1 | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Design%20Prototype%20v1.twbx | X | X | X | X |  |  | X |  | X |  | X | X | X
2015-06-20 | One | Decision Strategy | Sprint Planning | Data Analysis | Developed mapping of user stories to API data | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Design%20Delivery.docx |  | X | X | X |  |  | X |  |  |  |  | X
2015-06-20 | One | Decision Strategy | Sprint Planning | Data Analysis | Identified gaps in OpenFDA adverse drug event datasets | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/FAERS%20Variables%20ASCII%20Gaps.xls |  |  |  | X |  |  | X |  |  |  |  | X
2015-06-20 | One | Delivery | Scrum Meeting | Prototype | Develop design prototype v2 | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Design%20Prototype%20v2.twbx | X | X | X | X |  |  | X |  | X |  | X | X | X
2015-06-22 | One | Delivery | Scrum Meeting | Prototype | Develop design prototype v3 | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Design%20Prototype%20v3.twbx | X | X | X | X |  |  | X |  | X |  | X | X | X
2015-06-23 | One | Delivery | Scrum Meeting | Prototype | Develop design prototype v4 | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Design%20Prototype%20v4.twbx | X | X | X | X |  |  | X |  | X |  | X | X | X
2015-07-01 | One | Delivery | Scrum Meeting | Code | Access OpenFDA API data through R interface | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Extracting%20FDA%20API%20data%20through%20R%20(Code).txt | X | [10 empty] | X | X
2015-07-01 | One | Delivery | Scrum Meeting | Analytical Mockup | Access OpenFDA API data through R interface | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Event%20Count%20by%20Outcome%20Bar%20Chart.png | X | [10 empty] | X | X
2015-07-02 | One | Delivery | Scrum Meeting | Data Analysis | Scrape web data for correlating product label changes with adverse drug events using open source technology | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Portia%20scraping%20results.JPG | X |  | X | [8 empty] | X | X
2015-07-02 | One | Delivery | Scrum Meeting | Data Analysis | Develop correlation between drug combinations and adverse drug events | https://github.com/binarygroup/OpenFDADesign/blob/master/Datasets/Drug.Combination.Percentage.combine.csv | X | X | X | X |  |  | X |  |  |  |  | X | X
2015-07-07 | One | Delivery | Scrum Meeting | User Testing | Tested Design Prototype on several different mobile devices | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Mobile%20Accessibility%20Tests.docx | X | X | X | [8 empty] | X | X
2015-07-07 | One | Delivery | Sprint Review | Acceptance Criteria | Met with user SME to review and get feedback on Design Prototype and usability | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/Design%20Delivery.docx | X | X | X | [8 empty] | X
2015-07-07 | One | Delivery | Retrospect | Monitoring Instrument | Produced a burndown chart for Pools 1 and 2 showing user story and issue resolution over time | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/GSA%2018F%20Burndown%20Chart-Pools1-2.png |  |  | X | X | X | [6 empty] | X | X
2015-07-07 | One | Delivery | Retrospect | Monitoring Instrument | Produced a GANTT chart for Pools 1 and 2 showing work over time | https://github.com/binarygroup/OpenFDADesign/blob/master/Artifacts/gsa-agile-18f-b-p-gantt.png |  |  | X | X | X | [6 empty] | X | X

## Meta
Phases | Rituals | Artifacts | Tools | Pools
Discovery | User Story Development | Acceptance Criteria | Mozenda | One
Decision Strategy | Sprint Planning | Analytical Mockup | Tableau | Two
Delivery | Scrum Meeting | Architecture
Implementation | Sprint Review | Code
| Retrospect | Data Analysis
| Backlog Grooming | Database
| Release | Database Design
Decision
Enterprise Context
Installation Instructions
Interview
Monitoring Instrument
Plan
Product Backlog
Prototype
Script
Sprint Backog
Technology Stack
User Testing
Vision Statement