## Data
Date | Pool | ODEA Phase | Ritual | Artifact | Result | Link | Understand what people need | Address the whole experience, from start to finish | Make it simple and intuitive | Build the service using agile and iterative practices | Structure budgets and contracts to support delivery | Assign one leader and hold that person accountable | Bring in experienced teams | Choose a modern technology stack | Deploy in a flexible hosting environment | Automate testing and deployments | Manage security and privacy through reusable processes | Use data to drive decisions | Default to open
2015-06-18 | One | Discovery | User Story Development | Enterprise Context | Research FDA and regulatory burden issues and drivers | Discovery and Requirements Analysis | X | X |  |  |  | X | X |  |  |  |  | X
2015-06-18 | One | Discovery | User Story Development | Enterprise Context | Document preliminary context for persona and scenarios | Discovery and Requirements Analysis | X | X |  |  |  | X | X |  |  |  |  | X
2015-06-19 | One | Discovery | User Story Development | Enterprise Context | Meet with user SMEs | Discovery and Requirements Analysis | X | X | X |  |  | X | X |  |  |  |  | X
2015-06-19 | One | Discovery | User Story Development | Product Backlog | Developed initial product backlog | Discovery and Requirements Analysis | X | X | X |  |  | X | X |  |  |  |  | X
2015-06-20 | One | Decision Strategy | Sprint Planning | Data Analysis | Developed mapping of user stories to API data | Design Delivery |  | X | X | X |  |  | X |  |  |  |  | X
2015-07-02 | One | Delivery | Scrum Meeting | Data Analysis | Scrape web data for correlating product label changes with adverse drug events using open source technology | Portia Scraping Results | X |  | X | [8 empty] | X | X

## Meta
Phases | Rituals | Artifacts | Tools | Pools
Discovery | User Story Development | Acceptance Criteria | Mozenda | One
Decision Strategy | Sprint Planning | Analytical Mockup | Tableau | Two
Delivery | Scrum Meeting | Architecture
Implementation | Sprint Review | Code
| Retrospect | Data Analysis
| Backlog Grooming | Database
| Release | Database Design
Decision
Enterprise Context
Installation Instructions
Interview
Monitoring Instrument
Plan
Product Backlog
Prototype
Script
Sprint Backog
Technology Stack
User Testing
Vision Statement